## Sheet1
User Story Id | Userstory Name | Userstory step definition |  |  |  |  | Assinged To | Estimated Time | Actual Time | Status
User 001 | User Login | As a<type of user> | I want to <Perform some task> | So that I can <Achieve some goal> | Priority | Story Points | Ragul | 2 days | 1 day | Complete
|  | As a user | I want to log in using my email and password | So that I can access my account | High | 8 | Sachin | 1 day | 1 day | Complete
|  | As a user | I want to be able to reset my password | so I can regain access to my account. | High | 5 | Seshu | 3 days |  | InProgress
|  | As a user | I want to log in using my social media accounts | so, the user can login for their convience | High | 7 | Venkatesh | 4 days | 3 days | Complete
|  | As a user | I want to see an error message | if I enter invalid details, so I know to try again | Low | 8 | Priyanka | 8 hrs |  | Inprogress
|  | As a user | I want to receive a notification email | Whether, there's login a new device | High | 6 | Shallini | 1 day | 1/2 day | Complete
User 002 | Ticket Booking | As a user | I want to search flight by entering depart and dest. | So that I can able to select flight | Low | 5 | Sainadh | 1 day | 1 day | Complete
|  | As a user | I want to filter by price,dep time, availablity,.. | so that user can able to select per preference | Low | 8 | Mayank | 3 days | 3 days | Complete
|  | As a user | I want to sort search results by price, duration,time | so, the user can able to select per preference | Low | 4 | Venkatesh | 4 days |  | InProgress
|  | As a user | I want to review my details before confirming | so I can ensure everything is correct. | High | 7 | sathish | 8 hrs |  | InProgress
|  | As a user | make payments securely using my preferred method | so I can complete my booking | High | 8 | sai | 1 day | 1 day | Complete
|  | As a user | I want to receive a confirmation email | so I have proof of purchase and travel information. | High | 5 | mayank | 1 day | 1 day | Complete
User 003 | Payment | As a user | I want to enter my payment details securely | to complete my booking. | High | 4 | Sachin | 1 day | 1 day | Complete
|  | As a user | want see a summary of flight details and total cost | so I can verify the information. | High | 6 | Seshu | 3 days | 2 | Complete
|  | As a user | want the payment page to support multiple currency | so I can pay in my preferred currency. | High | 7 | Sainadh | 4 days | 4 days | Complete
|  | As a user | I want to apply discount codes or promotions | to reduce my total cost. | low | 6 | Priyanka | 8 hrs | 6 hrs | Complete
|  | As a user | I want to save my payment detail securely for future | so I don't have to enter them again. | High | 8 | Mayank | 1 day | 1 day | Complete
|  | As a user | I want to receive an immediate confirmation email | so I know my booking is confirmed. | High | 5 | Shallini | 1 day |  | InProgress
User 004 | Feedback | As a user | I want to provide a rating for booking experience | so I can share my satisfaction level. | High | 7 | Sachin | 1 day |  | InProgress
|  | As a user | I want to write a review of my booking experience | so I can give detailed feedback | low | 6 | Seshu | 3 days |  | InProgress
|  | As a user | I want to view other users' ratings and reviews | so I can make informed decisions about booking. | low | 4 | Venkatesh | 4 days | 3 days | Complete
|  | As a admin | I want to monitor and moderate user reviews | I can ensure arch is appropriate and constructive. | low | 8 | Sai | 8 hrs | 8 hrs | Complete
|  | As a user | I want to filter reviews by rating, date, and relevance | so I can quickly find the most useful feedback. | low | 7 | Shallini | 1 day | 1 day | Complete
|  | As a admin | I want to generate reports on user feedback | so I can identify trends and areas for improvement. | High | 4 | Shallini | 1 day | 1 day | InProgress
User 005 | Admin panel | As a admin | I want to log in securely to the admin panel | so I can access administrative functions. | High | 7 | Sachin | 1 day | 1 day | Complete
|  | As a admin | want to manage flight schedules (add, edit, delete) | can keep updated with current flight information. | High | 6 | Seshu | 3 days |  | InProgress
|  | As a admin | I want to view and manage user accounts | so I can provide support and handle issues. | High | 5 | Venkatesh | 4 days | 4 days | Complete
|  | As a admin | I want to view and manage bookings | so I can monitor & modify reservations as needed. | High | 7 | Priyanka | 8 hrs |  | InProgress
|  | As a admin | I want to receive alerts for critical system issues | so I can address them promptly. | High | 8 | ragul | 1 day | 1 day | Complete
|  | As a admin | I want to manage discount codes and promotions | so I can offer deals to users | High | 3 | mayank | 1 day | 1 day | Complete
|  | As a admin | I want to monitor system logs and user activity | so I can ensure security and compliance. | High | 6 | Nivas | 1 day | 1 day | Complete
|  | As a admin | I want to manage payment settings and gateways | so I can ensure smooth transaction processing. | High | 8 | Priyanka | 1 day |  | InProgress
User 004 | Booking Cancel | As a user | I want to log in to my account securely | so I can access my bookings | High | 7 | Sachin | 1 day |  | InProgress
|  | As a user | I want to view my current and past bookings | so I can select the booking I wish to cancel. | low | 6 | Seshu | 3 days |  | InProgress
|  | As a user | I want to select a booking and cancel it | so I can manage my travel plans | low | 5 | Venkatesh | 4 days | 3 days | Complete
|  | As a user | I want to see the cancellation policy and refund | so I can make an informed decision | low | 8 | Sai | 8 hrs | 8 hrs | Complete
|  | As a user | I want to receive a confirmation message and email | so I know the process is complete. | low | 7 | Shallini | 1 day | 1 day | Complete
|  | As a user | I want to track the status of my refund | so I know when to expect it | High | 4 | Shallini | 1 day | 1 day | InProgress

## Sheet 2
DEFECT ID | DEFECT | Created on | Creator | Assigned To | Severity | priority | Status
D001 | Unabe to search fights | jun-8-2024 | ragul | Sachin | High | High | Open
D002 | Unabe to make payments | may-27-2024 | priyanka | Shallini | High | High | Open
D003 | there's a spelling mistake in destination | june-1-2024 | mayank | rahul nivas | low | low | close
D004 | unable to upload profile picture | april-1-2024 | sachin | seshu | medium | low | Open
D005 | Notification messages not receiving | may-12-2024 | venkatesh | ragul | High | medium | close
D006 | Unable to register | may-20-2024 | glory | rahul nivas | High | medium | Open